## Sheet1
SMAT Upgrade Activities
S.No | Server | Activity Description | Sub Activities | Status
1 | DB | Database Backup from Old Production | 10.2 Database Backup | Sunday, December 19, 2024 7:07 PM
2 | DB | Install Smart Materials Database Software | Install SMAT DB Component
3 | DB | Database Server Installation | Install the Oracle Database Software
4 |  |  | Install Opatch
5 |  |  | Install Patches (35962832 & 35926646)
6 |  |  | Post Patch Install Steps
7 | DB | New Database Creation (SMATPRD) | Creation of new Pluggable Database
8 |  |  | SQL NET Configuration
9 |  |  | Creation of Tablespaces
10 |  |  | Import DTD File
11 |  |  | Configuring init.ora
12 |  |  | Connection Test from DB server and application servers | Tuesday, December 24, 2024
13 | DB | Database Backup from Old Production | 10.2 Database Backup
14 | DB | Import the Smart Materials Dump | Importing 10.2 data in new Database (SMAT PRD)
15 |  |  | Create APEX tablespaces
16 |  |  | Post Import scripts
17 |  |  | Analyze the database objects for errors
18 | DB | Install Apex 23.2 in the new Database | Install Apex23.2 in SMATPRD DB
19 |  |  | Install Apex Patch (35895964)
20 | DB | Smart Materials Upgrade to 10.5 | Create SMAT Web Workspace
21 |  |  | Run SMAT 10.5 Upgrade Scripts
22 |  |  | Post Uprgrade Steps
23 | License | Smart Materials License Service Installation | Install IIS Server with proper roles and features
24 |  |  | Configure ISL Client
25 |  |  | Install the Smart Materials License Webservice
26 |  |  | Test the Webservice
27 |  |  | Create ACL
28 |  |  | Create and Configure Oracle Wallet
29 |  |  | Configure the CIP m_sys.m_pck_http_custom for wallet
30 | Apex | Smart Materials Web Setup | Tomcat Installation and Configuration
31 |  |  | SMAT Web Component Installation
32 |  |  | Configure Apex to Support ORDS database
33 |  |  | Configure Apache Tomcat to support Apex
34 |  |  | ORDS Installation in Database
35 |  |  | Tomcat Security Configuration and SSL certificate installation
36 |  |  | Password and Session Timeout settings for BIR_SPMAT workspace
37 |  |  | Install Smart Materials Web Modules in Apex | Saturday, December 28, 2024 7:07 PM
38 | SRD Plus | Install IIS Server | Install IIS Server with proper roles and features
39 | SRD Plus | SSL Certificate for SRD Plus | Configure SSL for SRD Service in IIS Server
40 | SRD Plus | Oracle Client Installation | Install Oracle Client 19C
41 |  |  | Install Patch for Oracle Client (35962832)
42 |  |  | Register GAC Dlls
43 |  |  | TNS configuration and connection test to DB
44 | SRD Plus | SRD Plus Server Installation | Server Installation
45 |  |  | Modify Web Configuration
46 |  |  | Reference Data Client Installation
47 |  |  | Testing of Web Service and DB Connection from SRD Plus | Tuesday, December 31, 2024 5:06 PM
48 | Classic | SMAT Classic Installation | SMAT Classic Component Installation
49 | Classic | Repo DB Installation | Install Oracle DB (V982656-01)
50 |  |  | Install Opatch
51 |  |  | Install Patches (35962832 & 35926646)
52 |  |  | Configure Listener
53 |  |  | Repo DB Creation
54 |  |  | SQL NET Configuration and connection test to REPO DB
55 | Classic | Application Server Configuration | Configure Static IP
56 |  |  | Install Java JDK (Java SE Development Kit 8 Update 401 for 64-bit)
57 |  |  | Install Oracle Weblogic Server Patch (34519923) Version 12.2.1.4.0
58 |  |  | Install Forms and Reports
59 |  |  | Install Repository
60 |  |  | Install Oracle WLS Patch (28186730)
61 |  |  | Install Oracle Virtual Directory Generic (34065178) Version 12.2.1.4.0
62 |  |  | Install Oracle WLS Generic Bundle Patch (36178496) Version 12.2.1.4.240111
63 |  |  | Install Oracle SQL Developer Version 21.4.3.063.0100
64 |  |  | Prepare for Patch (35943354) installation
65 |  |  | Install Oracle Virtual Directory Generic (35943354) Version 12.2.1.4.0
66 |  |  | Install Oracle Forms 12.2.1.19.0 Interim Patch for Bug (36009429)
67 |  |  | Configure Fusion Middleware
68 |  |  | Disable the Derby Database
69 |  |  | Initialize the Admin Server
70 |  |  | Start NodeManager
71 |  |  | Start AdminServer
72 |  |  | Start Managed Servers
73 |  |  | Install Node Manager Service
74 |  |  | Reports Server Configuration
75 | Classic | Create Reports Tools and Server Instance | Create Reports Tools and Server Instance
76 |  |  | Enable Reports Web Access
77 |  |  | Disable Single Sign On
78 |  |  | Grant Access on Non-Default Directories
79 |  |  | Start Report Tools
80 |  |  | Start Report Instance
81 | Classic | OHS Configuration | Start OHS
82 |  |  | OHS Listing Port Configuration
83 |  |  | Configure OHS
84 | Classic | Module Configuration | Configure sqlnet.ora and tnsnames.ora
85 |  |  | Configure Formsweb.cfg
86 |  |  | Configure Default.env
87 |  |  | Configure Oracle Web Start
88 |  |  | Check Forms and Reports Mapping
89 | Classic | Install WebUtil | Web Util Installation
90 |  |  | Check Configuration | Wed 1/1/2025 10:42 AM
91 | WPF | IIS Configuration | Install IIS Server with proper roles and features
92 | WPF | Oracle Client Installation | Install Oracle Client 19C
93 |  |  | Install Patch for Oracle Client (35962832)
94 |  |  | Register GAC Dlls
95 |  |  | TNS configuration and connection test to DB
96 | WPF | Install Smart Materials WPF | Install the Smart Materials IIS Application Server
97 |  |  | Run Post Installation Scripts
98 | WPF | Secure Socket Layer (SSL) Configuration | SSL Configuration
99 |  | Smart Materials Portal Configuration | Enable Portal Login | Tuesday, December 31, 2024 6:09 PM

## Sheet2
SMAT Upgrade Activities
S.No | Activity Description | Sub Activities | Status
1 | Configure Roles for new Menus | Add the new Agreement/Expiditing Menus for all required Roles
2 | Configure DBA Settings for SMTP Email | Change SMTP_Client DBA Setting