## Slide 1
SMAT Forecast Run
Date: Sep 2025
Organizer: Sherif A. Moneim

## Slide 2
  Overview
  Work package
  Material allocation levels
  Forecast report
  Forecast shortage receipt notifications
SMAT Forecast Run
Index
Index

## Slide 3
  Forecasting Key Features
    Simulate materials availability
    Plan project work and subcontractor needs
    Reserve materials in advance (virtually)
    Early alert for material shortages
    Simple conversion from virtual to actual reservations
    Material receiving notifications for forecasting shortage items
SMAT Forecast Run
Overview
For larger projects, it's important to know specific details in advance for the planning process, figuring out which materials can be prefabricated or installed by certain dates, and to check the material already in transit (shipped items), purchase orders and approved requisitions be delivered by the specified date.
Notes: For larger projects, it's important to know specific details in advance for the planning process, figuring out which materials can be prefabricated or installed by certain dates, and to check the material already in transit (shipped items), purchase orders and approved requisitions be delivered by the specified date
Forecast Run (FR) tool. It helps simulate when materials will be available for construction or fabrication, making it easier to plan project work and subcontractor needs. Running a forecast does not impact actual inventory or material quantities.
•After running the Forecast, the system reserve material virtually for the selected Work-package items with completion status percentage, the allocation result that can be converted later to actual reservation.
•The result contains the estimated Dia

## Slide 4
Achievement
SMAT Forecast Run
  Forecasting Prerequisites
    Purchased material cycle
    Bill of Materials
    Warehouses are defined
    Work packages
    User permissions
  Forecasting material Allocation
Overview
Purchased Materials
(Eng. MTO + Contingency)
Allocation
Work Package

## Slide 5
Achievement
SMAT Forecast Run
  What is a work package
    A work package is a user-defined selection of Bill of Materials that allows you to specify a focused scope of work. Essentially, a work package breaks down a larger project into manageable sections for easier planning, tracking, and control.
  Work package examples
    Shutdown BOM
    Tie-In BOM
    BOM without hold
    A specific material
    Early phase
    Issued isometrics for a specific area
    Pipe racks and sleepers
    Hydrotest loop isometrics
Work Package

## Slide 6
Achievement
SMAT Forecast Run
Material Allocation Levels
Work Package

## Slide 7
Achievement
SMAT Forecast Run
    Report Data
      Predicated and actual Dia-inch Workfront chart
      Allocation level Dia-inch summary
      DWG completion status and percentage
Forecast Report

## Slide 8
Achievement
SMAT Forecast Run
Forecast Report

## Slide 9
Achievement
SMAT Forecast Run
Forecast Report

## Slide 10
Achievement
SMAT Forecast Run
Forecast Shortage Receipt Notifications
Notes: automated alerts generated when materials are received that are needed to address a previously forecasted shortage. These notifications inform users in real-time that critical materials projected to be in short supply have now arrived

## Slide 11: Forecast Run(FR)
For larger projects, it's important to know specific details in advance for the planning process, figuring out which materials can be prefabricated or installed by certain dates, and to check the material already in transit (shipped items), purchase orders and approved requisitions be delivered by the specified date
Forecast Run (FR) tool. It helps simulate when materials will be available for construction or fabrication, making it easier to plan project work and subcontractor needs. Running a forecast does not impact actual inventory or material quantities.

## Slide 12: Material Allocation
Purchased Materials
Allocation
Work Package
Notes: -Allocate purchased materials to Construction work package
-

## Slide 13: Material Allocation Levels
Work Package

## Slide 14
Work package
Idents and list positions are the two important concepts to understand before working with work packages.
What is an ident?
A commodity code is an alphanumeric string that is built according to user-definable rules.
An example is PCB100AAXXA each letter or number represents a specific attribute except dimensional information.
Size/ Sch.

## Slide 15: What are Nodes and list positions?
A node is the smallest unit of a hierarchy structure that is linked to one another to define the architecture
(i.e., Unit >> Area >>Fluid >> LineId >> Iso.).
List positions are the positions that are assigned to nodes and describe the ident and property details of that node.
List position = MTO item ( Ident with Qty).

## Slide 16
What is a work package
A work package is a user-defined selection of BOM nodes and materials that allows you to define specific Where conditions for the ident and list position selection (scope of material).
They are used in a forecast and reservation run to determine the material that is required to perform scheduled construction tasks.
Where Conditions
So what are these Where conditions?
Where conditions allow you to have a limited view of the database content.
For example, you define where conditions to select specific material from the available material list while performing any audit or process.
We have five types of where conditions available that can be used or selected while creating a work package.

## Slide 17
Where Conditions
So what are these Where conditions?
Where conditions allow you to have a limited view of the database content.
For example, you define where conditions to select specific material from the available material list while performing any audit or process.
We have five types of where conditions available that can be used or selected while creating a work package.

## Slide 18
Material Where Condition
Through this condition, you can limit the idents (material) to be selected from the BOM by the forecast/reservation run.
BOM Where Condition
Through this condition, you can limit the WBS nodes and BOM list positions to be selected from the BOM by the forecast/reservation run.
e Condition
Mandatory Material Where Condition
Through this condition, you can define a set of specific material (mandatory list positions) that is necessary for starting the installation. This where condition is used by the forecast/reservation run shortage option.

## Slide 19: Work package workflow